# IoT Telemetry & Auto-Scaling Engine: Task Breakdown

Team task list for a two-person project, split into a local track and an Azure track · Created 27 Oct 2026 · Case study: city-wide seismic and structural monitoring network

## How to use this document

- Owner values: Local is the person on the local track, Azure is the person who holds the Azure for Students subscription, Both is a pair task (do it together on a call or side by side), and Board owner is whoever has the ESP32. Replace Local and Azure with your names.

- Reviewer: every task is reviewed by the other person through a GitHub pull request. Work on a branch, never directly on main.

- Depends on means do not start until those tasks are Done. IDs starting with K are kickoff, L are local track, Z are Azure track, E are final testing.

- Status: use To do, In progress, In review or Done.

- Weeks follow the six-week plan in the proposal. Shift them to fit your course schedule.

## Team split

The local track needs no cloud account, so it can start on day one. The Azure track starts with a smoke test of the student subscription, then packages and deploys what the local track builds.

| Track | Owner | Covers | Needs Azure credit? |
| --- | --- | --- | --- |
| Local | Local | ESP32 and gateway, simulator core, Ingest API and Processor code, local RabbitMQ and TimescaleDB, local Kubernetes with kind, HPA and self-healing on that cluster | No |
| Azure | Azure | Azure account and AKS, Dockerfiles, docker-compose, tests, CI/CD, Prometheus and Grafana, two simulator features, cloud deployment, cost control | Yes, except Z6 to Z14 and Z17 |

Both of you still learn both technologies. The Azure owner writes the Dockerfiles and the Local owner writes the Kubernetes manifests, and the first of each is a pair task followed by a teach-back. The Azure owner's tasks Z6 to Z14 need no Azure access, so they keep going even if the subscription turns out to be restricted.

## Shared kickoff (Week 1)

| ID | Task | Owner | Depends on | Done when | Status |
| --- | --- | --- | --- | --- | --- |
| K1 | Create the GitHub repo, invite the other person, accept the invite | Local | none | Both can push a branch and merge a pull request | Done |
| K2 | Install tools: Git, Docker Desktop, kubectl, kind (or k3d), Python 3.11+, VS Code; the Azure owner also installs the Azure CLI | Both | none | docker run hello-world and kubectl version --client work on both laptops | Done |
| K3 | Create the folder layout, .gitignore (include .env, kubeconfig files and Azure credentials) and a README skeleton | Local | K1 | Merged to main | Done |
| K4 | Agree working rules: branch per task, PR review, commit message style, weekly sync day | Both | K1 | Rules written in a Contributing section of the README | Done |
| K5 | Write a one-page problem statement for the seismic monitoring case study | Azure | none | Page saved in docs/ | Done |
| K6 | Define the message format: device_id, batch_id (unique ID), measured_at, sent_at, is_backfill, summary or waveform payload | Local | K5 | Schema file reviewed by the Azure owner | Done |
| K7 | Define the Ingest API contract: endpoint, API-key header, responses 202, 400, 401, 429 | Local | K6 | Contract written down and reviewed | Done |
| K8 | Write the minute-by-minute scenario timeline: normal day, small tremor, earthquake, outage, backlog flush, calm-down, with node counts and requests per second | Azure | K5 | Timeline table in docs/, used later to size the cloud cluster | Done |
| K9 | Draw the architecture diagram with live and backfill queues, dead-letter queue, idempotency and the Azure parts (AKS, registry, load balancer) | Azure | K6, K8 | Diagram image in docs/ | Done |

## Local track: no Azure needed

Everything here runs on your own laptop. Owner is Local unless marked.

### Edge and simulator (Weeks 1 to 2)

| ID | Task | Owner | Depends on | Done when | Status |
| --- | --- | --- | --- | --- | --- |
| L1 | ESP32: read the accelerometer at a fixed rate and keep a local buffer | Board owner | none | Readings print over serial at the expected rate | To do |
| L2 | ESP32: local trigger on a shaking threshold; send a summary every minute and a raw waveform window when triggered | Board owner | L1 | Shaking the board switches it from summary to raw upload | To do |
| L3 | Gateway script: receive ESP32 data, batch it, send over HTTPS with an API key, buffer locally and retry with jittered backoff | Local | K7 | Survives the server being down and sends the backlog on return | In progress |
| L4 | Simulator: one virtual device with a fixed-rate waveform generator (low noise normally, decaying oscillation for an event) | Local | K6 | Generated waveform looks like noise, then shaking | Done |
| L5 | Simulator: summary mode and raw mode, batching, unique batch ID per batch | Local | L4 | One device can send both kinds of batches to a test server | Done |
| L6 | Simulator: fleet manager using asyncio; ramp from 50 to 500 devices with random joins and leaves | Local | L5 | 500 devices run on one laptop without the laptop being the bottleneck | Done |
| L7 | Simulator: scenario controller that reads a YAML timeline (quake, outage, aftershocks) | Local | L5, Z10, K8 | Changing the YAML changes the traffic pattern | Done |

### Microservices (Week 2)

| ID | Task | Owner | Depends on | Done when | Status |
| --- | --- | --- | --- | --- | --- |
| L8 | Ingest API skeleton: POST endpoint, JSON validation, /healthz and /readyz | Local | K7 | Valid batch gets 202, invalid gets 400 | Done |
| L9 | Ingest API: per-device API-key authentication (401) and backpressure (429 with Retry-After) | Local | L8 | Wrong key is rejected; overload returns 429 instead of failing | Done |
| L10 | Run RabbitMQ locally; create live and backfill queues (live has priority) and a dead-letter queue | Local | none | Messages routed to the right queue; bad ones land in the dead-letter queue | Done |
| L11 | Ingest API publishes validated batches to the live or backfill queue | Local | L9, L10 | Batch appears in the correct queue | Done |
| L12 | Run TimescaleDB locally; create tables for readings, summaries and events with a unique constraint on batch_id | Local | K6 | Tables created by a migration script | Done |
| L13 | Processor: consume the queues (live first), compute RMS, peak and FFT per batch | Local | L10, L12 | Results stored in the database | Done |
| L14 | Processor: ignore duplicate batch IDs, send failing messages to the dead-letter queue | Local | L13 | Resending a batch creates no duplicate rows | Done |
| L15 | Processor: event detection that checks whether many nearby nodes triggered within a time window; skip real-time alerts for backfill data | Local | L14 | Simulated quake produces one event; a single triggered node does not | Done |
| L16 | Graceful shutdown in both services: finish the current message when told to stop | Local | L11, L14 | Stopping a container mid-load loses no messages | Done |

### Local Kubernetes (Weeks 3 to 4)

| ID | Task | Owner | Depends on | Done when | Status |
| --- | --- | --- | --- | --- | --- |
| L17 | Create a local cluster with kind or k3d and load the images | Local | Z6, Z7 | kubectl get nodes shows Ready | Done |
| L18 | First Deployment and Service for the Ingest API, with CPU and memory requests and limits plus liveness and readiness probes (do it together) | Both | L17 | Two replicas running; both can explain every field | Done |
| L19 | Deployment and Service for the Processor with requests, limits and probes | Local | L18 | Replicas consume from RabbitMQ in the cluster | Done |
| L20 | Run RabbitMQ and TimescaleDB in the cluster with persistent storage, ConfigMaps and Secrets | Local | L17 | Data survives a database pod restart | Done |
| L21 | Expose the Ingest API, point the simulator at it and confirm data reaches the database | Local | L18, L19, L20 | Simulated readings appear in the database | Done |
| L22 | Install metrics-server | Local | L17 | kubectl top pods shows values | Done |
| L23 | HPA for the Ingest API (start with min 2, max 10, target CPU 60%) | Local | L22, L18 | HPA shows current and target CPU | Done |
| L24 | HPA for the Processor (same starting values) | Local | L22, L19 | Replicas rise when queue work increases | Done |
| L25 | Add service metrics: requests per second, 429 count, queue depth, processing latency | Local | L21 | Metrics visible in Prometheus once Z13 is up | Done |
| L26 | Self-healing test: delete a pod during load and check no messages are lost | Both | L23, L24 | Replacement starts quickly; message count matches | In progress |
| L27 | Measure a baseline and tune the HPA thresholds; record scale-out time | Local | L26, Z14 | Numbers written in a results table | In progress |
| L28 | Teach-back on Kubernetes: explain pod, ReplicaSet, Deployment and Service to each other; delete a pod by hand and watch it return | Both | L26 | Both can answer without notes | In progress |

## Azure track: Azure, Docker and DevOps

Start with Z1 to Z5 in Week 1, because the whole cloud plan depends on the smoke test. Owner is Azure unless marked. Azure for Students has tight limits (see Risks), so keep every cluster small.

### Azure setup and smoke test (Week 1)

| ID | Task | Owner | Depends on | Done when | Status |
| --- | --- | --- | --- | --- | --- |
| Z1 | Activate Azure for Students with the college email; confirm the $100 credit and note which regions the subscription allows | Azure | none | Credit visible in the Azure portal; allowed regions written down | Done |
| Z2 | Set a budget alert on the subscription; do not upgrade to pay-as-you-go | Azure | Z1 | Alert email received on a test threshold | Done |
| Z3 | Register the AKS resource provider (Microsoft.ContainerService) and check the vCPU quota in an allowed region | Azure | Z1 | Quota numbers written down | Done |
| Z4 | Smoke test: create the smallest possible AKS cluster, run a sample container, expose it through a load balancer, then delete the cluster | Azure | Z3 | Go or no-go decision recorded with the region, VM size and cost per hour | Done |
| Z5 | Write a one-page Azure runbook: region, VM size, create, stop and delete commands, how the other person gets kubectl access | Azure | Z4 | Page saved in docs/ and reviewed by the Local owner | Done |

### Docker, tests and simulator parts (Weeks 2 to 3, no Azure needed)

| ID | Task | Owner | Depends on | Done when | Status |
| --- | --- | --- | --- | --- | --- |
| Z6 | Write the Dockerfile for the Ingest API (first Dockerfile, do it together) | Both | L8 | docker build and docker run work; both can explain each line | Done |
| Z7 | Write the Dockerfile for the Processor | Azure | L13 | Container processes messages from the queue | Done |
| Z8 | docker-compose.yml running the whole stack: Ingest API, Processor, RabbitMQ, TimescaleDB, Grafana | Azure | Z6, Z7, L10, L12 | One command brings the full pipeline up and data flows end to end | Done |
| Z9 | Unit tests: validation, authentication, duplicate handling, RMS calculation | Azure | L9, L14 | Tests pass locally; bugs reported to the Local owner | Done |
| Z10 | Simulator: link up/down state, capped local buffer, backlog flush marked is_backfill | Azure | L5 | A device goes offline, buffers, then sends the backlog on reconnect | Done |
| Z11 | Simulator: heartbeats aligned to minute boundaries and a jitter on/off switch | Azure | L6 | Traffic spikes at :00 with jitter off and flattens with jitter on | Done |
| Z12 | Teach-back on Docker: explain image vs container and each Dockerfile's layers to each other | Both | Z7 | Both can answer without notes | In progress |

### Monitoring (Weeks 3 to 4)

| ID | Task | Owner | Depends on | Done when | Status |
| --- | --- | --- | --- | --- | --- |
| Z13 | Install Prometheus and Grafana on the local cluster | Azure | L17 | Grafana opens and reads Prometheus | Done |
| Z14 | Grafana dashboard: messages per second, queue depth, replica count, latency | Azure | L25, Z13 | One screen tells the spike story | Done |

### Registry and CI/CD (Weeks 3 to 5)

| ID | Task | Owner | Depends on | Done when | Status |
| --- | --- | --- | --- | --- | --- |
| Z15 | Create a container registry (Azure Container Registry, or GitHub's registry if you want to save credit) and push a test image | Azure | Z4 | Image visible in the registry | Done |
| Z16 | Practice on AKS with a sample app: Deployment, Service, HPA and deleting a pod; stop the cluster when idle | Azure | Z4 | Written notes on what worked | Done |
| Z17 | GitHub Actions workflow that runs the tests on every push | Azure | Z9 | Green check on a pull request | Done |
| Z18 | Workflow step that builds both Docker images and pushes them to the registry | Azure | Z17, Z15 | New image appears after a merge to main | Done |
| Z19 | Store credentials in GitHub Actions secrets; confirm nothing secret is in the repo | Azure | Z18 | Secret scan of the repo finds nothing | In progress |
| Z20 | Workflow step that deploys to AKS with a rolling update | Azure | Z18, Z22 | Merge to main updates the live pods | Done |
| Z21 | Automatic rollback when the rollout fails its health probes | Azure | Z20 | A deliberately broken image is rolled back | Done |

### Cloud deployment (Weeks 4 to 6)

| ID | Task | Owner | Depends on | Done when | Status |
| --- | --- | --- | --- | --- | --- |
| Z22 | Create the project cluster with small nodes within the quota (enable node autoscaling if the subscription allows it) and give the Local owner kubectl access | Azure | Z4 | Both can run kubectl get nodes against it | Done |
| Z23 | Deploy the full stack to AKS using the Local owner's manifests | Both | Z22, L21, Z18 | Pipeline works end to end in the cloud | Done |
| Z24 | Expose through the Azure load balancer and point the simulator and gateway at the public address | Azure | Z23 | Simulator sends data from a laptop to the cloud | Done |
| Z25 | Node-level scaling demo: fill the nodes, see pods stay Pending, then a new node appear; if quota blocks it, record the limit instead | Azure | Z23 | Behaviour or limit captured with screenshots | In progress |
| Z26 | Optional: run the simulator inside AKS as a Job if the laptop becomes the bottleneck | Azure | Z24 | Higher load reached than from the laptop | Done |
| Z27 | Zero-downtime release demo: push a change while the simulator is running | Both | Z20, Z21, Z24 | No failed requests in the simulator log | In progress |
| Z28 | Cost watch: check remaining credit every week, stop the cluster when idle, delete it after demos, and write a teardown checklist | Azure | Z22 | Billing page shows no running resources after the final demo | Done |

## Handoff points

The two tracks depend on each other at these points. Check this table at every weekly sync, and pair up if a handoff is more than two days late.

| When | From | To | What is handed over |
| --- | --- | --- | --- |
| End of Week 1 | Local (K6, K7) | Azure | Message format and API contract, used for tests and for sizing the cluster |
| End of Week 1 | Azure (Z4, Z5) | Both | Go or no-go on AKS, with region, VM size, quota and cost per hour |
| Week 2 | Local (L8, L13) | Azure | Working Ingest API and Processor code, ready to be packaged and tested |
| Week 2 to 3 | Azure (Z6 to Z8) | Local | Dockerfiles and a docker-compose.yml that runs the whole stack |
| Week 3 | Local (L18 to L21) | Azure | Kubernetes manifests that work on the local cluster |
| Week 4 | Azure (Z22) | Local | kubectl access to the AKS cluster |
| Week 5 | Both (Z23, Z24) | Both | Full stack running on AKS and reachable from the simulator |

## Final testing and demo (Week 6)

| ID | Task | Owner | Depends on | Done when | Status |
| --- | --- | --- | --- | --- | --- |
| E1 | Test: traffic spike on AKS, replicas increase and no messages are lost | Both | Z24, L27 | Results and screenshots saved | In progress |
| E2 | Test: scale-in, replicas return to the minimum after the cooldown | Both | E1 | Scale-in time recorded | In progress |
| E3 | Test: reconnect storm; live data drains before backfill | Local | L7, L13 | Queue panel shows live drained first | In progress |
| E4 | Experiment: thundering herd with jitter off versus on | Azure | Z11 | Two graphs side by side | In progress |
| E5 | Test: duplicate batch, malformed batch and wrong API key | Local | L14 | Database has no duplicates; bad batch parked; wrong key rejected | In progress |
| E6 | Test: self-healing during a full scenario run | Local | L26 | Service stays available | In progress |
| E7 | Test: end to end with the real ESP32 (shake the board, watch Grafana) | Board owner | L2, Z24 | Live values appear in Grafana | In progress |
| E8 | Collect all results into one table with screenshots | Both | E1 to E7 | Table in docs/ | In progress |
| E9 | Write the final report: the Local owner covers case study, edge, services and local Kubernetes; the Azure owner covers cloud, CI/CD and cost; cross-review each other | Both | E8 | Report complete and cross-reviewed | To do |
| E10 | Write the demo script and rehearse it; record a backup video in case the live demo fails | Both | E8 | Two full rehearsals done | To do |
| E11 | Final cleanup: tidy README, remove unused files, delete all cloud resources | Azure | E10, Z28 | Fresh clone runs with the README, and Azure billing shows no running resources | To do |

## Milestones

| Week | Milestone | You are done when |
| --- | --- | --- |
| 1 | Repo, tools, contract and scenario ready; Azure smoke test decided | K1 to K9 and Z1 to Z5 are Done |
| 2 | Services and simulator run in Docker Compose | L3 to L6, L8 to L16 and Z6 to Z8 are Done |
| 3 | Same pipeline runs on local Kubernetes; first practice on AKS | L17 to L21, Z15 and Z16 are Done |
| 4 | Auto-scaling and monitoring work locally; CI pipeline running | L7, L22 to L28, Z9 to Z14 and Z17 to Z19 are Done |
| 5 | Full stack running on AKS with automated deployment | Z20 to Z24 are Done |
| 6 | Tests run, report written, demo rehearsed | Z25 to Z28 and E1 to E11 are Done |

## Be ready to explain

These are the questions most likely to come up in the viva. Each of you should be able to answer all of them.

- Why does one sensor not need auto-scaling, and what makes the load vary in your case study?

- Why do live data and backfill data go through different queues?

- What does HPA scale, and what happens when the nodes themselves are full?

- What is the difference between an image and a container?

- What does the cloud do with seismic data at each time scale, and what does your project not do?

- What happens to a node's data when connectivity is lost, and what is the buffer limit?

## Risks to watch

- Azure limits: student subscriptions are reported to have restricted regions, low vCPU quotas and no quota increases, and errors like "Not available for subscription" are common. Run the smoke test (Z4) in Week 1 and size the cluster small.

- Credit running out: the $100 must cover nodes, load balancer and registry, and once it is gone you must renew or upgrade to pay-as-you-go. Set the budget alert first, stop the cluster when idle and delete it after demos.

- One subscription: only the Azure owner holds it, so agree early how the Local owner gets kubectl access (Z22), and keep a runbook (Z5) so either of you can recreate the cluster.

- Waiting on the other track: if a handoff is more than two days late, pair on it. Z6 to Z14 need no Azure access, so the Azure owner is never idle.

- Azure falls through: if the smoke test is a no-go, finish everything else locally and document in the report how the same manifests deploy to AKS.

- Simulator limits: if the laptop saturates before the cluster does, run the simulator inside AKS as a Job (Z26).